## Start Here
Annual Planning Workbook
How to fill it in (in this order)
1. Settings | Plan year, focus factor, holidays, and the dropdown lists (roles, statuses, categories).
2. Objectives | 3–5 objectives for the year with a measurable key result each.
3. Projects | One row per initiative: objective, priority, size, dates, owners. Effort & labor cost auto-fill.
4. Team | Everyone supplying capacity, incl. contractors and Open Req placeholders with start dates.
5. Allocation | Person × project × month as a fraction of their time. This is the heart of resource planning.
6. Milestones / RAID | Committed dates, decision gates, risks and dependencies.
7. Review | Dashboard → gaps & over-allocation; Capacity → who's red; Roadmap → sequencing.
Colour legend
Yellow cell, blue text | Input — type here.
Grey cell | Formula — don't overwrite.
Green text | Pulled from another tab.
Planning tips
Plan to ~85% not 100% | The focus factor reserves time for support, meetings and unplanned work.
Use Open Req rows | Plan the work first; the role gap on the Dashboard becomes your hiring ask.
Rank, don't just tag | If demand > capacity, cut from the bottom of P3/P4 — make the trade-off visible in the meeting.
Quarterly re-plan | Re-forecast Allocation each quarter; keep the yearly view as the baseline copy.
Power BI
Data source | Get Data → Excel → pick tables tblProjects, tblTeam, tblAllocation, tblMilestones, tblRAID, tblObjectives.
Allocation months | In Power Query select Jan–Dec on tblAllocation → Unpivot Columns → gives Month/Allocation rows.
Blank rows | Filter each table on its ID/Name column ≠ blank (template rows are pre-built).
Relationships | tblProjects[ID] → tblAllocation[Project ID], tblMilestones, tblRAID; tblTeam[Name] → tblAllocation[Resource].
Sample data | All rows are illustrative examples — overwrite or delete them (keep the formula columns).

## Dashboard
Plan Summary
Plan year 2027 • all effort in FTE-months (1 = one person for one month)
Active projects | P1 projects | Demand (FTE-mo) | Staffed capacity | Open-req capacity | Gap (staffed − demand) | People >100% in any month | Open high risks | Total budget
3 | 1 | 52.2 | 49.3122 | 7.1965 | -2.8878 | 6 | 0 | 706800
Capacity vs demand by month
Month | Staffed capacity | Open-req capacity | Demand | Gap (staffed − demand) | Team utilization
2027-01-01 | 4.0868 | 0 | 3.7 | 0.38684 | 90.53%
2027-02-01 | 4.0868 | 0 | 3.7 | 0.38684 | 90.53%
2027-03-01 | 4.1227 | 0 | 4.6 | -0.47727 | 111.6%
2027-04-01 | 4.1227 | 0.8017 | 5.4 | -1.2773 | 109.7%
2027-05-01 | 4.1 | 0.79688 | 4.8 | -0.7 | 98.02%
2027-06-01 | 4.1119 | 0.7994 | 4.8 | -0.6881 | 97.73%
2027-07-01 | 4.1119 | 0.7994 | 4.8 | -0.6881 | 97.73%
2027-08-01 | 4.1227 | 0.8017 | 4.8 | -0.67727 | 97.47%
2027-09-01 | 4.1119 | 0.7994 | 3.9 | 0.2119 | 79.41%
2027-10-01 | 4.1119 | 0.7994 | 3.9 | 0.2119 | 79.41%
2027-11-01 | 4.1 | 0.79688 | 3.9 | 0.2 | 79.64%
2027-12-01 | 4.1227 | 0.8017 | 3.9 | 0.22273 | 79.2%
Total | 49.3122 | 7.1965 | 52.2 | -2.8878 | 92.38%
Supply vs demand by role (annual FTE-months)
Role | Staffed supply | Open-req supply | Demand | Gap (staffed − demand)
Engineering Manager | 0 | 0 | 0 | 0
Tech Lead | 8.8299 | 0 | 9.2 | -0.37008
Architect | 0 | 0 | 0 | 0
Backend Developer | 9.3818 | 0 | 8.4 | 0.98179
Frontend Developer | 10.3668 | 7.1965 | 18 | -7.6332
Full-stack Developer | 10.3668 | 0 | 7.6 | 2.7668
QA / SDET | 10.3668 | 0 | 9 | 1.3668
DevOps / SRE | 0 | 0 | 0 | 0
Business Analyst | 0 | 0 | 0 | 0
Product Owner | 0 | 0 | 0 | 0
Scrum Master | 0 | 0 | 0 | 0
UX Designer | 0 | 0 | 0 | 0
Portfolio mix by category
Category | # Projects | FTE-months | % of demand |  | Status | # Projects
Run / KTLO | 1 | 2.4 | 4.598% |  | Proposed | 1
Grow | 1 | 5.4 | 10.34% |  | Approved | 1
Transform | 1 | 44.4 | 85.06% |  | In Progress | 1
Compliance / Risk | 0 | 0 | 0% |  | On Hold | 0
Tech Debt | 0 | 0 | 0% |  | Done | 0
[5 empty] | Cancelled | 0

## Objectives
Objectives & Key Results
What the year is for. Every project should ladder up to one objective.
Obj ID | Objective | Key Result | Target | Owner | # Projects | Planned FTE-months
O1 | Modernize legacy platforms | Legacy JSP/Struts screens retired | 60% | Siva | 1 | 44.4
O2 | Improve reliability & operational visibility | Reduction in P1/P2 incidents YoY | 30% | Siva | 2 | 7.8
O3 | Deliver priority business features | Roadmap commitments shipped on time | 90% |  | 0 | 0

## Projects
Project Portfolio
One row per project. Effort and labor cost fill in automatically from the Allocation tab. Sample rows — overwrite.
ID | Project | Objective ID | Category | Priority | Size | Business Owner | Tech Lead | Start | End | Status | RAG | Planned FTE-months | Labor cost | Non-labor budget | Total budget | Key dependencies | Success measure / notes
P001 | RepApp Angular migration (strangler fig) | O1 | Transform | P1 | XL |  | Tech Lead 1 | 2027-01-04 | 2027-12-17 | In Progress | Green | 44.4 | 580800 | 0 | 580800 | Contractor continuity; TBH Angular dev by Apr | Phase 1–2 screens live; JSP decommission decision by Nov
P002 | Application portfolio dashboard | O2 | Run / KTLO | P2 | M | Manager peer group | Tech Lead 1 | 2027-01-11 | 2027-04-30 | Approved | Amber | 2.4 | 34400 | 5000 | 39400 | SNOW + Jira API access | Dashboard adopted by peer managers
P003 | Observability & alerting uplift | O2 | Grow | P2 | M |  | Java Dev 1 | 2027-03-01 | 2027-08-31 | Proposed | Green | 5.4 | 66600 | 20000 | 86600 | Platform team logging standards | Alert baseline in prod; MTTR down

## Roadmap
Annual Roadmap
Bars come from project Start/End dates; ◆ = milestone in that month. Sorted as entered on Projects.
[6 empty] | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4
ID | Project | Priority | Status | Start | End | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
P001 | RepApp Angular migration (strangler fig) | P1 | In Progress | 2027-01-04 | 2027-12-17 |  |  | ◆ |  |  |  | ◆ |  |  |  | ◆
P002 | Application portfolio dashboard | P2 | Approved | 2027-01-11 | 2027-04-30 |  |  | ◆
P003 | Observability & alerting uplift | P2 | Proposed | 2027-03-01 | 2027-08-31 | [5 empty] | ◆

## Team
Team & Resources
Everyone who supplies capacity — FTEs, contractors, and open reqs (to show hiring need). Sample rows — overwrite.
Name | Role | Type | Vendor / Org | Primary skills | Location | Availability % | PTO days / yr | Start date | End date | Monthly cost rate | Annual capacity (FTE-mo) | Annual allocated (FTE-mo) | Utilization | Notes
Tech Lead 1 | Tech Lead | FTE | Fidelity | Java, Spring Boot, AWS | Raleigh | 80% | 20 |  |  | 15000 | 8.8299 | 9.2 | 104.2% | • Availability % = time for project work (focus factor). Blank uses Settings default.
Java Dev 1 | Backend Developer | FTE | Fidelity | Java, Kafka | Raleigh | 85% | 20 |  |  | 12000 | 9.3818 | 8.4 | 89.54% | • Blank start/end = full plan year. Use them for new joiners and contractor roll-offs.
Angular Dev 1 | Frontend Developer | Contractor | InRhythm | Angular, TypeScript | Remote | 90% | 10 |  |  | 14000 | 10.3668 | 10.8 | 104.2% | • Monthly cost rate is a placeholder — use loaded/blended rates from Finance.
Angular Dev 2 | Full-stack Developer | Contractor | InRhythm | Angular, Java | Remote | 90% | 10 |  |  | 14000 | 10.3668 | 7.6 | 73.31% | • Open Req rows let you plan work for people not hired yet.
QA Engineer 1 | QA / SDET | Contractor | InRhythm | Playwright, API testing | Remote | 90% | 10 |  |  | 11000 | 10.3668 | 9 | 86.82%
TBH Angular Dev | Frontend Developer | Open Req | Fidelity | Angular | Raleigh | 85% | 15 | 2027-04-01 |  | 12000 | 7.1965 | 7.2 | 100%

## Allocation
Resource Allocation
One row per person × project. Enter the share of that person's month (0.5 = 50%). Sample rows — overwrite.
Resource | Role | Project ID | Project | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | FTE-months | Monthly rate | Labor cost
Tech Lead 1 | Tech Lead | P001 | RepApp Angular migration (strangler fig) | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 7.2 | 15000 | 108000
Tech Lead 1 | Tech Lead | P002 | Application portfolio dashboard | 20% | 20% | 20% | 20% | [8 empty] | 0.8 | 15000 | 12000
Tech Lead 1 | Tech Lead | P003 | Observability & alerting uplift |  |  | 20% | 20% | 20% | 20% | 20% | 20% |  |  |  |  | 1.2 | 15000 | 18000
Java Dev 1 | Backend Developer | P001 | RepApp Angular migration (strangler fig) | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 6 | 12000 | 72000
Java Dev 1 | Backend Developer | P003 | Observability & alerting uplift |  |  | 40% | 40% | 40% | 40% | 40% | 40% |  |  |  |  | 2.4 | 12000 | 28800
Angular Dev 1 | Frontend Developer | P001 | RepApp Angular migration (strangler fig) | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 10.8 | 14000 | 151200
Angular Dev 2 | Full-stack Developer | P001 | RepApp Angular migration (strangler fig) | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 6 | 14000 | 84000
Angular Dev 2 | Full-stack Developer | P002 | Application portfolio dashboard | 40% | 40% | 40% | 40% | [8 empty] | 1.6 | 14000 | 22400
QA Engineer 1 | QA / SDET | P001 | RepApp Angular migration (strangler fig) | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 7.2 | 11000 | 79200
QA Engineer 1 | QA / SDET | P003 | Observability & alerting uplift |  |  | 30% | 30% | 30% | 30% | 30% | 30% |  |  |  |  | 1.8 | 11000 | 19800
TBH Angular Dev | Frontend Developer | P001 | RepApp Angular migration (strangler fig) |  |  |  | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 7.2 | 12000 | 86400

## Capacity
Capacity & Utilization
Fully calculated — no inputs. Red = over-allocated (>100%), amber = under 50%.
Utilization (allocated ÷ capacity)
Name | Role | Type | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | Peak month | Annual | 999% = work allocated in a month the person isn't available (before start / after end date).
Tech Lead 1 | Tech Lead | FTE | 109.6% | 109.6% | 135.2% | 135.2% | 109.1% | 108.6% | 108.6% | 108.2% | 81.47% | 81.47% | 81.82% | 81.15% | 135.2% | 104.2%
Java Dev 1 | Backend Developer | FTE | 64.48% | 64.48% | 114.6% | 114.6% | 115.5% | 115% | 115% | 114.6% | 63.89% | 63.89% | 64.17% | 63.65% | 115.5% | 89.54%
Angular Dev 1 | Frontend Developer | Contractor | 104.6% | 104.6% | 103.9% | 103.9% | 104.3% | 104.1% | 104.1% | 103.9% | 104.1% | 104.1% | 104.3% | 103.9% | 104.6% | 104.2%
Angular Dev 2 | Full-stack Developer | Contractor | 104.6% | 104.6% | 103.9% | 103.9% | 57.97% | 57.85% | 57.85% | 57.74% | 57.85% | 57.85% | 57.97% | 57.74% | 104.6% | 73.31%
QA Engineer 1 | QA / SDET | Contractor | 69.72% | 69.72% | 103.9% | 103.9% | 104.3% | 104.1% | 104.1% | 103.9% | 69.42% | 69.42% | 69.57% | 69.29% | 104.3% | 86.82%
TBH Angular Dev | Frontend Developer | Open Req |  |  |  | 99.79% | 100.4% | 100.1% | 100.1% | 99.79% | 100.1% | 100.1% | 100.4% | 99.79% | 100.4% | 100%
Capacity (FTE available per month)
Name | Role | Type | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | Total FTE-mo
Tech Lead 1 | Tech Lead | FTE | 0.72982 | 0.72982 | 0.73939 | 0.73939 | 0.73333 | 0.73651 | 0.73651 | 0.73939 | 0.73651 | 0.73651 | 0.73333 | 0.73939 | 8.8299
Java Dev 1 | Backend Developer | FTE | 0.77544 | 0.77544 | 0.78561 | 0.78561 | 0.77917 | 0.78254 | 0.78254 | 0.78561 | 0.78254 | 0.78254 | 0.77917 | 0.78561 | 9.3818
Angular Dev 1 | Frontend Developer | Contractor | 0.86053 | 0.86053 | 0.86591 | 0.86591 | 0.8625 | 0.86429 | 0.86429 | 0.86591 | 0.86429 | 0.86429 | 0.8625 | 0.86591 | 10.3668
Angular Dev 2 | Full-stack Developer | Contractor | 0.86053 | 0.86053 | 0.86591 | 0.86591 | 0.8625 | 0.86429 | 0.86429 | 0.86591 | 0.86429 | 0.86429 | 0.8625 | 0.86591 | 10.3668
QA Engineer 1 | QA / SDET | Contractor | 0.86053 | 0.86053 | 0.86591 | 0.86591 | 0.8625 | 0.86429 | 0.86429 | 0.86591 | 0.86429 | 0.86429 | 0.8625 | 0.86591 | 10.3668
TBH Angular Dev | Frontend Developer | Open Req | 0 | 0 | 0 | 0.8017 | 0.79688 | 0.7994 | 0.7994 | 0.8017 | 0.7994 | 0.7994 | 0.79688 | 0.8017 | 7.1965
Allocated (FTE per month, from Allocation)
Name | Role | Type | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | Total FTE-mo
Tech Lead 1 | Tech Lead | FTE | 0.8 | 0.8 | 1 | 1 | 0.8 | 0.8 | 0.8 | 0.8 | 0.6 | 0.6 | 0.6 | 0.6 | 9.2
Java Dev 1 | Backend Developer | FTE | 0.5 | 0.5 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.5 | 0.5 | 0.5 | 0.5 | 8.4
Angular Dev 1 | Frontend Developer | Contractor | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8
Angular Dev 2 | Full-stack Developer | Contractor | 0.9 | 0.9 | 0.9 | 0.9 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 7.6
QA Engineer 1 | QA / SDET | Contractor | 0.6 | 0.6 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.6 | 0.6 | 0.6 | 0.6 | 9
TBH Angular Dev | Frontend Developer | Open Req | 0 | 0 | 0 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 7.2

## Milestones
Milestones & Key Dates
Releases, decision gates and dates you've committed to. They show as ◆ on the Roadmap.
Project ID | Project | Milestone | Target date | Quarter | Type | Owner | Status | Notes
P002 | Application portfolio dashboard | MVP dashboard to manager peers | 2027-03-15 | Q1 | Release | Tech Lead 1 | Not Started
P001 | RepApp Angular migration (strangler fig) | Phase 1 screens live behind strangler proxy | 2027-03-31 | Q1 | Release | Tech Lead 1 | On Track
P003 | Observability & alerting uplift | Alerting baseline in production | 2027-06-30 | Q2 | Milestone | Java Dev 1 | Not Started
P001 | RepApp Angular migration (strangler fig) | Phase 2 screens live | 2027-07-30 | Q3 | Release | Tech Lead 1 | Not Started
P001 | RepApp Angular migration (strangler fig) | Legacy JSP decommission decision | 2027-11-15 | Q4 | Decision Gate | Siva | Not Started

## RAID
Risks, Assumptions, Issues & Dependencies
Score = probability × impact (1–5 each). High ≥ 15, Medium ≥ 8.
ID | Type | Project ID | Description | Probability (1-5) | Impact (1-5) | Score | Severity | Owner | Mitigation / next step | Due | Status
R001 | Risk | P001 | Contractor roll-off or attrition slows Angular migration | 3 | 4 | 12 | Medium | Siva | Pair FTE with each contractor; document modules | 2027-02-28 | Open
A001 | Assumption | P001 | TBH Angular developer onboarded by April | 3 | 4 | 12 | Medium | Siva | Open req approved in Q4; backup: extend InRhythm SOW | 2027-01-31 | Open
D001 | Dependency | P002 | SNOW + Jira API access approved | 3 | 3 | 9 | Medium | Tech Lead 1 | Raise access request in January | 2027-01-29 | Open

## Settings
Settings & Lists
Edit yellow cells. Lists feed every dropdown in the workbook — add/rename values here.
Plan year | 2027
Default availability (focus factor) | 85% | Share of a person's time available for project work after meetings, support, admin. Used when Team availability is blank.
Month start | Working days | Quarter | Holiday date | Holiday | Project Status | Priority | Category | Size | RAG | Resource Type | Role | RAID Type | RAID Status | Milestone Status | Milestone Type
2027-01-01 | 19 | Q1 | 2027-01-01 | New Year's Day | Proposed | P1 | Run / KTLO | S | Green | FTE | Engineering Manager | Risk | Open | Not Started | Milestone
2027-02-01 | 19 | Q1 | 2027-01-18 | MLK Day | Approved | P2 | Grow | M | Amber | Contractor | Tech Lead | Assumption | Mitigating | On Track | Release
2027-03-01 | 22 | Q1 | 2027-02-15 | Presidents' Day | In Progress | P3 | Transform | L | Red | Open Req | Architect | Issue | Closed | At Risk | Decision Gate
2027-04-01 | 22 | Q2 | 2027-03-26 | Good Friday | On Hold | P4 | Compliance / Risk | XL |  |  | Backend Developer | Dependency |  | Late | Dependency Due
2027-05-01 | 20 | Q2 | 2027-05-31 | Memorial Day | Done |  | Tech Debt |  |  |  | Frontend Developer |  |  | Done
2027-06-01 | 21 | Q2 | 2027-06-18 | Juneteenth (observed) | Cancelled | [5 empty] | Full-stack Developer
2027-07-01 | 21 | Q3 | 2027-07-05 | Independence Day (observed) | [6 empty] | QA / SDET
2027-08-01 | 22 | Q3 | 2027-09-06 | Labor Day | [6 empty] | DevOps / SRE
2027-09-01 | 21 | Q3 | 2027-11-25 | Thanksgiving | [6 empty] | Business Analyst
2027-10-01 | 21 | Q4 | 2027-11-26 | Day after Thanksgiving | [6 empty] | Product Owner
2027-11-01 | 20 | Q4 | 2027-12-24 | Christmas (observed) | [6 empty] | Scrum Master
2027-12-01 | 22 | Q4 | [8 empty] | UX Designer
Sample US 2027 dates — replace with your company holiday calendar.
Formulas:
Working days = NETWORKDAYS([Month start],EOMONTH([Month start],0),E8:E30)