## Slide 1
DOMAIN REVIEW • SEPTEMBER 8, 2026
Application Modernization
From an undefined scope to a shippable slice — and what lands on Sep 30
Director of Software Engineering
Notes: Open with the frame: I took this over four weeks ago. Here is exactly what I found, what I changed, what it cost us, and what you will see on Sep 30. No surprises at the end of this deck.

## Slide 2
What I picked up on Aug 10
Project started in January. I joined seven months in, with a Sep 30 production date already set.
1
No scope on paper
The team had a verbal ask — modernize two pages — and no written definition of done.
2
Modify, not modernize
Work in flight was editing the legacy pages rather than migrating them cleanly.
3
Skill mix off-balance
Almost entirely front-end developers on a project that needed backend depth.
4
Knowledge gap on APIs
The developer who built the supporting APIs had left the team.
Notes: Be factual, not blaming. The point is that the delivery risk was structural, not effort-related. Nobody was under-working; the project had no defined finish line.

## Slide 3
Weeks 1–2: put a floor under the project
Five moves, before writing a single line of plan for leadership.
1
Evaluated the team
Mapped every developer's real strength against what the project actually needed.
2
Rebalanced the skill mix
Moved several front-end developers onto backend work to close the API gap.
3
Pulled Product in
Product now answers open functional questions directly, instead of the team guessing.
4
Brought in an SDET
Owns the quality checklist and the test plan — quality defined up front, not at the end.
5
Set milestones to Sep 30
Broke the goal into assigned, dated milestones so progress became measurable.
Notes: This is the credibility slide. Say it plainly: in two weeks the team had the right shape, a quality owner, a product partner, and dated milestones. Then pause - because the next slide says it still was not enough.

## Slide 4
Weeks 3–4: the honest read
The structure was right. The pace still was not.
Milestones missed
The team could not hit the dates we set together.
Half-cooked code
Work in progress across several flows, none of it finished to a releasable state.
Open questions
Functional gaps across several contribution types, still unanswered.
Four weeks in, I had a choice: hold the original scope and hope, or cut to something we can actually finish.
Notes: Do not soften this. Leaders trust the person who reports the miss before they have to ask. Say the number of weeks left out loud, then move straight into the decision - do not linger here.

## Slide 5
The call: one flow, finished end to end
I cut scope to what the team can complete and release with confidence.
ORIGINAL SCOPE
Two pages modernized in full
Every contribution type in scope
No written definition of done
Release process untested by the team
SCOPE FOR SEP 30
All supporting backend APIs delivered
Front end: Check contribution only
Quality checklist and test plan owned by SDET
Every decision and discussion documented
Notes: Frame it as a trade, not a retreat: we trade breadth for a finished, releasable vertical slice. The backend work is not reduced - the front-end surface is. That is deliberate.

## Slide 6
How the rest lands
Check contribution is the template. Every type after it gets cheaper.
SEP 30
Release 1
Full backend API set + Check contribution front to back, through the real release process.
OCT
Release 2
Next contribution types added onto a proven pattern and a tested pipeline.
NOV +
Scale out
Remaining contribution types and pages absorbed at an increasing rate.
Sep 30 is not the whole product — it is the first real proof that this team can ship it.
Notes: This answers the obvious leadership question - what happened to the rest of it. Nothing is dropped; it is sequenced behind a proven pattern.

## Slide 7
Why a narrow first release is the right call
What the team gains that a wider, unfinished scope would not have given us.
Release muscle
The team runs the full release management process once, on a small surface, before it matters at scale.
A repeatable pattern
Check contribution becomes the reference implementation for every contribution type behind it.
Backend risk retired
All supporting APIs ship now, so front-end work later is assembly, not discovery.
A written record
Discussions, decisions and evidence documented — the scope gap that started this no longer exists.
Notes: This is the slide that converts a descope into a strategy. Land the phrase: we are buying a strong base, not buying time.

## Slide 8
Where confidence sits — and what I need
Straight read, four weeks out from the date.
Watching closely
Team velocity is still unproven against a real release date
Open functional questions can still reopen scope
First pass through the release process always costs more than planned
What I'm asking for
Endorse the reduced Sep 30 scope as the committed scope
Keep Product available for fast answers through September
Hold the release window — no new asks before Oct 1
Notes: Never end a status story without an ask. Three specific ones, all cheap for them to grant, all things that genuinely protect the date.

## Slide 9
Where we stand
Confidence is still building. But the team now has everything it needs to deliver something meaningful on Sep 30.
Defined scope. The right skills. A quality owner. A product partner. A written record. And one flow we will finish.
Notes: Close on ownership, not on hope. Last line delivered slowly. Then stop talking and take questions.