## Slide 1
Decision brief · Rep application
The app: finish, rebuild, or reset?
How to take a 25-year-old rep application the rest of the way, and what to build on top of it once it's one system.
Siva · Director of Software Engineering
Product and Engineering leadership review · September 2026
Notes: Purpose today: agree on how we decide, not just what we decide. We're asking for a six-week discovery and pre-agreed decision rules, then a gate.

## Slide 2
Where we are
One application, two experiences, and a decision that has been made by default for eight months.
25 yrs
since the app was first built on Struts; later collapsed into one Spring Boot app
45 / 55
percent of features in the new Angular experience vs. still in legacy
8 mo
of migration so far, started with no written scope
2
user interfaces a rep crosses to finish one customer task
The pain we feel
Builds fail new CI/CD quality gates unpredictably; Sonar and security findings pile up in legacy code
New features take longer than they should because every change inherits legacy risk
Nobody can say which features reps value and which should change
Reps say they don't like the new experience, and the split makes it inconsistent
The question we were asked
Finish migrating the remaining 55%, or overhaul and build a new application?
The caveats that came with it: users may not like a new experience, and a new app takes time.
App modernization · Decision brief · 2
Notes: Set the context in a minute. The important line is the last one: the question as asked is binary, and the rest of the deck argues that it shouldn't be.

## Slide 3
Symptoms on top, five problems underneath
A rewrite addresses two of them and makes the fourth worse.
Parity migration with no product thesis
The team was asked to "modernize two pages." Parity produces an old app in a new framework, and it's why nobody can say which features we like.
Two experiences for one job
Half-migrated is the worst state, not a midpoint. Every task that crosses the boundary pays a context-switch tax.
The legacy module taxes every change
Unpredictable gates mean new-stack work inherits legacy risk from the same repo and pipeline. Fixable in weeks, independent of the big decision.
Knowledge has already leaked
The API author is gone; 25 years of business rules live in code. This is the strongest argument against a blank-page rewrite.
Decisions by opinion, not evidence
No usage data, no rep task data, no effort-per-feature data. Any call made today is a debate between anecdotes.
App modernization · Decision brief · 3
Notes: Problem 4 is the one to land: a rewrite rediscovers undocumented business rules one production incident at a time, and we've already lost the person who knew them.

## Slide 4
The rep signal is our most important input
Each plausible cause points to a different fix, and to a different answer on the big question.
Hypothesis | What it looks like | What it implies for the decision
Built for consumers, used by operators | Whitespace, wizards, one thing per screen. Reps want density, keyboard flow, several things visible at once. | Both "finish" and "rebuild" fail unless the design language changes.
The split itself | Complaints cluster on tasks that cross old and new: re-login, lost context, searching twice. | Cure is consistency and speed of convergence, not starting over.
Lost power features | Parity missed shortcuts, bulk actions and side-by-side views nobody wrote down. | Restore in the new stack; observe reps, don't survey them.
Performance | New screens are measurably slower for common tasks. | Engineering fix in the current stack; no change of direction.
Change management | Reps weren't involved, trained or told why. | Cheap process fix that de-risks every path.
In practice it's usually two or three of these together. The first is the one most often missed in enterprise modernizations, and it's the one that sinks greenfield rebuilds: the new app repeats the same pattern, a year later, at three times the cost.
App modernization · Decision brief · 4
Notes: The point of this slide: we cannot choose a direction until we know which of these is true. Discovery names the cause.

## Slide 5
Three options, compared honestly
The two on the table plus the one we think the evidence will lead to.
A · Finish the 55% as parity
Keep migrating feature by feature until legacy is empty. Same approach, more months.
Time to one experience
Mixed
~10 months at measured pace, then redesign
Rep acceptance
Weak
Ships more of what reps dislike
Reuse of the 45%
Strong
Full
Knowledge risk
Strong
Low
New features meanwhile
Weak
Blocked
Right when: Product's only priority is speed and the rep issue turns out to be performance or training.
B · Greenfield new app
New product from a blank page, run in parallel until cutover.
Time to one experience
Weak
18–30 months for a system this old
Rep acceptance
Mixed
Unknown; same failure mode at higher cost
Reuse of the 45%
Weak
Little
Knowledge risk
Weak
High; rules rediscovered in production
New features meanwhile
Weak
Frozen; two codebases
Right when: Discovery finds the domain model or APIs are wrong for where the business is going.
C · Reset the strangler
Keep modernized APIs. Retire dead features. Rebuild the experience as one shell designed with reps. Migrate only what earns it.
Time to one experience
Strong
One shell in a quarter; converge in 3–4
Rep acceptance
Strong
Grounded in rep observation
Reuse of the 45%
Strong
APIs full, UI partial
Knowledge risk
Mixed
Moderate; retire only with proof
New features meanwhile
Strong
New stack only; migrate on touch
Right when: Any other outcome. This is the default.
App modernization · Decision brief · 5
Notes: Option C is a 'new modern app' from the rep's and stakeholder's point of view, without paying to rewrite the parts nobody sees. Two heuristics for the room: Brooks's second-system effect and the Netscape 6 rewrite.

## Slide 6
Product's priority should choose the path
Scored under each of the three candidate priorities. One option holds under all three.
If Product's priority is… | A · Finish parity | B · Greenfield | C · Reset | What C looks like under this priority
Time: one experience, fast | Viable with scope cuts | Slowest | Best | Lite reset: unified shell in Q4, retire aggressively, migrate the rest as-is except the top five rep complaints. Two to three quarters.
Experience: reps love the tool | Fails by definition | Possible, costly | Best | Full reset: experience principles and design system first, task-based redesign of top workflows, legacy converges behind it. Three to four quarters.
New features: serve customers in new ways | Blocks feature work | Freezes feature work | Best | New-stack-only rule for all new capability; legacy migrates on touch. The conversational layer (slide 11) lands here, on the documented donor-flow APIs.
Option C is the default not because it's the boldest, but because it's the only option that doesn't have to bet on which priority Product picks. We still want Product to pick one: it sets how much redesign we do and how fast we converge.
App modernization · Decision brief · 6
Notes: Ask Product directly here: which of the three is it? The answer changes the roadmap on slide 10 but not the recommendation.

## Slide 7
The remaining 55% is a portfolio, not a backlog
Every feature gets one of five dispositions before anyone writes code. Only two of the five are engineering work.
Retire
No usage in 90 days or a workaround exists. Flag off, watch, delete.
Typical share 20–30%
Reuse
An equivalent exists elsewhere in the enterprise. Integrate, after checking it fits rep workflow.
Typical share 10–15%
Retain
Rare but required (compliance, edge case). Freeze, reach from the new shell, sunset with a date.
Typical share 10–15%
Rebuild
Used, works, nobody wants it changed. Port as-is with automated parity tests.
Typical share 20–30%
Redesign
High-frequency, high-friction rep tasks. Where the design effort and rep co-creation go.
Typical share 15–25%
Shares are planning assumptions from comparable long-lived internal tools; discovery replaces them with the app numbers. The point: engineering scope is usually 40–55% of the nominal feature count, which changes the time estimate for every option. The same exercise runs over the migrated 45%.
App modernization · Decision brief · 7
Notes: If someone wants to keep 'finish the 55%' as the plan, this is how to finish it well: retire first, then the 55% is a lot smaller.

## Slide 8
Six weeks of discovery before we commit
Two to three people, separate from the September 30 delivery. Each track ends in a written artifact the decision gate consumes.
Weeks 0–2
Stabilize
New-code Sonar profile; legacy module isolated as its own build stage; security findings triaged with AppSec into fix-now / fix-by-date / accept.
Output A build the team can trust; a debt register
Weeks 1–3
Evidence
Feature inventory at rep-task level (first draft generated from code); 90 days of usage from access logs and HAR captures; defect history; enterprise capability scan.
Output Inventory with usage; first-pass disposition
Weeks 2–4
Reps
Contextual inquiry with 6–8 reps, 90 min each, watching real customer work across both UIs; two sessions on the migrated 45%; top-tasks survey after observation; recruit rep champions.
Output Journey map; root cause; experience principles
Weeks 3–5
Architecture & velocity
API coverage map per rep task; target architecture (shell + BFF + existing APIs); velocity baseline from the last 8 months applied to every option; knowledge-risk register.
Output Costed options in quarters and people
Weeks 5–6
Synthesis
Final disposition counts and effort; A/B/C costed with assumptions listed; recommendation, roadmap, kill criteria per quarter.
Output Decision pack for the gate
App modernization · Decision brief · 8
Notes: Stabilization starts this month regardless of the decision. The rep track is the one we can least afford to do badly; that's why we're asking for a UX partner.

## Slide 9
Decision rules, written before the evidence
So the gate is a decision, not a rerun of this debate.
Choose B · Greenfield only if
The API coverage map shows modernized APIs serve less than a third of top rep tasks, AND the redesign bucket exceeds ~60% of live features, AND Product's priority is experience with a multi-year funding commitment.
All three, not any one.
Choose A · Finish parity only if
The rep root cause is performance or change management, retirement removes at least a quarter of the remaining scope, and Product's priority is time with no appetite for redesign.
Then A becomes "A with retirement," which is C-lite by another name.
Otherwise · C · Reset
Any other combination. The roadmap on the next slide assumes this outcome; if the gate chooses differently, the discovery artifacts still feed the alternative.
Gate date: end of week 6 of discovery, with whatever evidence exists. The gate happens on the date; discovery does not expand to fill it.
App modernization · Decision brief · 9
Notes: This is the ask that matters most today: agree to these rules now.

## Slide 10
Roadmap for the default path
Each quarter has a rep-visible outcome and a stop condition, so the program can be ended or redirected at a boundary.
Q4 2026
One front door
Unified Angular shell: single login, navigation, search and customer context across both stacks. Design system with rep experience principles. Top five complaints on the migrated 45% fixed. First retirements behind flags. New-stack-only rule in force.
Reps see The app feels like one application even though two run underneath.
Stop or redirect if Rep task time on migrated screens doesn't improve after fixes.
Q1 2027
Top tasks, redesigned
Redesign bucket in order of rep frequency, co-designed with rep champions. Rebuild bucket ported with parity tests. Reuse integrations landed. Retirements confirmed and deleted.
Reps see The tasks reps do most are measurably faster and stay in one place.
Stop or redirect if Velocity falls below the discovery baseline for two sprints.
Q2 2027
Convergence
Remaining rebuild items. Retain bucket reachable from the shell but frozen. Legacy module read-only and off the main pipeline.
Reps see Reps rarely see a legacy screen; when they do, it's inside the same shell.
Stop or redirect if More than a handful of retired features come back.
Q3 2027
Decommission
Retain items migrated or sunset. Legacy runtime removed. Debt register closed. Program ends. Conversational layer pilot begins on the converged APIs.
Reps see One application. Feature requests get built, not scheduled around a migration.
Stop or redirect if None; this is the finish line by design.
App modernization · Decision brief · 10
Notes: Duration assumes discovery retires or reuses 25–40% of the remaining scope. If retirement comes in low, add a quarter rather than compress the redesign; compressing redesign is how we got the current rep reaction.

## Slide 11
After convergence: a conversational layer over the same APIs
Reps ask the app to do things. The model chooses the API and fills the fields; code validates; the rep confirms; the API executes.
Chat in Angular
Rep types "contribute $5,000 by check for the Patel giving account." Streams the reply; renders a confirmation card.
Orchestration service
Server-side (Spring AI). Calls Fidelity's approved LLM endpoint. The browser never talks to the model.
Domain model ("ontology")
Entities, actions, required fields, eligibility rules, permissions, expressed as tool schemas. Policies in a retrieval index.
Deterministic validation
Code checks amounts, account status, contribution rules. The model extracts; it never bypasses a business rule.
Rep confirms, API executes
Called with the rep's own token, so authorization matches the UI. Prompt, parameters, confirmation and response are audited.
Why it's worth doing
Removes multi-step, cross-feature work from the rep's hands while keeping every safeguard the UI has. Start read-only (lookups, explain this account, summarize history); add write actions with confirmation once trusted. It also gives the modernization a better finish line than parity: every rep action becomes an API.
What it depends on
Clean, documented APIs for each flow (the contribution flows already qualify, so a pilot can start early). An enterprise LLM endpoint. Model Risk and compliance approval, prompt-injection and PII controls, evaluation suites and audit logging. At Fidelity the governance is the long pole, not the code.
App modernization · Decision brief · 11
Notes: Angular is the smallest part of this. The intelligence, validation and audit live server-side, and the model never calls an API without a rep confirming the card. Sequencing: pilot on the documented donor-flow APIs as soon as governance allows, expand as convergence completes.

## Slide 12
What we're asking for today
Agreement on how we decide, and the resources to gather the evidence.
1
Agree the decision rules
The gate criteria on slide 9, before discovery starts.
2
A product owner for the app
Who commits to one of the three priorities by the gate and owns the retire list.
3
Six weeks and three people
One legacy-literate engineer, one UX partner (part-time is fine), and me; no capacity taken from September 30.
4
Access to reps and data
6–8 reps for 90 minutes each, arranged through their managers; 90 days of access logs; AppSec time in week one.
5
Start stabilization now
New-code quality profile and legacy build isolation this month, whichever way the decision goes.
App modernization · Decision brief · 12
Notes: Close on the ask. If we get these five, the next time we're in this room we bring numbers instead of opinions.