## Slide 1
Continue modernizing: what it gives us, what it costs
Finish the app as one Angular application over backend APIs, then add a conversational layer. The honest case on both sides.
Positives
One consistent experience Reps work in a single interface with one login, one navigation and one customer context. The split, which reps dislike most, goes away.
Keeps what already works The modernized APIs and 45% of migrated features are reused in full. Business rules move behavior by behavior, so 25 years of tacit logic isn't rediscovered in production.
Predictable delivery Freezing and isolating legacy makes builds pass reliably within weeks; feature-by-feature migration lets us ship, measure and redirect each quarter.
Foundation for AI Every rep action becomes an API. That is exactly what a chat layer needs to validate, confirm and execute a contribution safely on the rep's behalf.
New features stay possible New capability goes only into the new stack while legacy migrates on touch, so the program doesn't freeze the roadmap.
Negatives and how we handle them
Reps dislike the current new UI If we migrate without fixing the cause, we ship more of the problem. Mitigation: observe reps first, set experience principles, redesign the top tasks with rep champions.
Time to converge Roughly a year at measured velocity even after retiring dead features; legacy and new run side by side until then. Mitigation: one unified shell in the first quarter so it feels like one app early.
Knowledge risk The API author has left; undocumented rules could be lost mid-migration. Mitigation: behavior specs per feature and pairing on the legacy code now.
Debt doesn't vanish on day one Sonar and security findings shrink as features retire or move, not immediately. Mitigation: new-code quality profile and a dated debt register.
AI layer has a long governance pole Model risk, compliance, PII and audit approvals will take longer than the code. Mitigation: start read-only, pilot on the documented contribution APIs.
App modernization · Summary · 1
Notes: The negatives are real but each has a mitigation that is already in the plan. The one that decides the program is the first: we have to name why reps dislike the new experience before we build more of it.

## Slide 2
The plan
Stabilize now, decide on evidence in six weeks, converge in four quarters, then put a conversational layer on the APIs.
Now
Stabilize
New-code Sonar profile; legacy isolated in its own build stage; security findings triaged with AppSec. Builds become predictable this month.
Weeks 1–6
Discover
Feature inventory with 90-day usage; every feature sorted into retire / reuse / retain / rebuild / redesign; 6–8 reps observed at work; velocity baseline and costed options.
Week 6
Decision gate
Pre-agreed rules pick the path: finish, rebuild, or reset. Product commits to a priority: time, experience, or new features.
Q4 2026
One front door
Unified Angular shell: single login, navigation, customer context across both stacks. Top five rep complaints fixed. First retirements.
Q1–Q2 2027
Converge
Top rep tasks redesigned with rep champions; the rest ported with parity tests; reuse integrations landed; legacy read-only.
Q3 2027
Decommission + AI pilot
Legacy runtime removed. Conversational layer pilots on the contribution APIs: chat extracts, code validates, rep confirms, API executes.
Operating rules for the program
Written scope and a named product owner No feature enters a sprint without a disposition.
Reps in the definition of done A redesigned task is done when rep champions complete it faster than in legacy.
Legacy frozen, isolated, dated New work goes only in the new stack; legacy migrates on touch.
Measure what reps feel Task time for the top ten rep tasks, reported monthly with the debt register.
App modernization · Summary · 2
Notes: Two decisions are needed from leadership: agree the gate rules now, and pick a product priority by week six. Everything else is engineering's to execute.