## Start Here
Portfolio Planner
One row per project. Weekly columns across the year, grouped into four 13-week quarters.
How it works
1. Set the start date | On the Setup tab, enter the Monday that week 1 of your plan begins. Every date, quarter band and Gantt bar in the workbook shifts to match.
2. List your people | Also on Setup: names and roles. These feed the Lead dropdown and the People Load tab.
3. Enter projects | On Year Plan, fill the shaded columns: project, program, lead, team, status, start and end dates. The bar draws itself.
4. Read the quarter | Quarter View shows 13 weeks at a time. Change the quarter number in the yellow cell to flip between Q1-Q4. Nothing else to touch.
5. Check the load | People Load counts how many projects each person is on, week by week. Amber means two at once, red means three or more.
What to edit
Shaded cells | Every cell you type into is shaded pale yellow. Everything else is a formula - leave it alone and it stays correct.
Adding rows | Insert rows inside the existing block (between the first and last project rows) so the formatting and formulas carry over.
More people | Add names in the Setup list and copy the last row of People Load down.
Bar colours
Not started | Scoped but no work yet.
On track | Will land on the committed date.
At risk | Date is threatened; a decision or help is needed.
Off track | Date has moved or will move. Escalated.
Complete | Delivered to production.
Worth knowing
Quarters | Quarters here are 13-week blocks counted from your start date, so they line up with sprints rather than with calendar month ends.
Team names | Type team members exactly as they appear in the Setup list, separated by commas. People Load matches on that spelling.
Circulating it | Nothing links to an outside file, so the workbook travels intact over email or SharePoint.

## Setup
Setup
Change these and the whole workbook follows.
Plan title | Engineering Portfolio 2026-27
Week 1 starts (Monday) | 2026-09-07 | 52 weeks are drawn from here
People |  |  | Lists
Name | Role |  | Status | Program / portfolio
Priya Nathan | Tech lead |  | Not started | Modernization
Marcus Bell | Senior engineer |  | On track | Regulatory
Dana Okafor | Senior engineer |  | At risk | Growth
Ravi Menon | Engineer |  | Off track | Platform / infra
Ellen Vargas | Engineer |  | Complete | Run the business
Tom Whitfield | SDET
Grace Lin | UX |  | Fixed list - shared with the colour rules.
Omar Haddad | Engineer

## Year Plan
Engineering Portfolio 2026-27
Yearly view - one row per project, one column per week
 | time axis 2026-09-07 to 2027-08-30
[11 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
[11 empty] | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Aug
# | Project | Program | Lead | Team (comma separated) | FTE | Status | Start | End | % done | Notes | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
1 | RepApp modernization - remaining 55% | Modernization | Priya Nathan | Priya Nathan, Marcus Bell, Dana Okafor, Tom Whitfield | 4 | At risk | 2026-09-07 | 2027-03-05 | 45% | Strangler migration to Angular; scope cut to check contribution first | [52 empty] | ,PriyaNathan,MarcusBell,DanaOkafor,TomWhitfield, | bar: Q1 Sep to Q2 Mar
2 | RepApp backend API hardening | Modernization | Marcus Bell | Marcus Bell, Ravi Menon | 2 | On track | 2026-09-07 | 2026-12-04 | 60% | Owner left; rebuild API knowledge and docs | [52 empty] | ,MarcusBell,RaviMenon, | bar: Q1 Sep to Q1 Nov
3 | Application portfolio dashboard | Run the business | Dana Okafor | Dana Okafor, Ellen Vargas | 1.5 | On track | 2026-09-21 | 2026-11-20 | 70% | Excel inventory feeding Power BI for the manager group | [52 empty] | ,DanaOkafor,EllenVargas, | bar: Q1 Sep to Q1 Nov
4 | Rep chat assistant - discovery | Growth | Grace Lin | Grace Lin, Omar Haddad | 1 | Not started | 2026-12-14 | 2027-04-09 | 0% | Ontology layer and in-app chat for donor flows | [52 empty] | ,GraceLin,OmarHaddad, | bar: Q2 Dec to Q3 Apr
5 | Quality gate remediation | Platform / infra | Tom Whitfield | Tom Whitfield, Ravi Menon | 1 | On track | 2026-09-07 | 2027-01-29 | 30% | Sonar findings and CI/CD build stability | [52 empty] | ,TomWhitfield,RaviMenon, | bar: Q1 Sep to Q2 Jan
6 | Sample row - delete me | Regulatory | Ellen Vargas | Ellen Vargas, Omar Haddad | 0.5 | Complete | 2026-09-07 | 2026-10-23 | 100% | Shows the format the workbook expects | [52 empty] | ,EllenVargas,OmarHaddad, | bar: Q1 Sep to Q1 Oct
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
,,
Active projects |  | 4 | At risk or off track |  | 1 | Total FTE booked | 10

## Quarter View
Engineering Portfolio 2026-27
Quarter | 1 | Weeks 1 to 13 ¦ 07 Sep 2026 - 06 Dec 2026
[7 empty] | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Project | Lead | Team | Status | Start | End | % done | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
RepApp modernization - remaining 55% | Priya Nathan | Priya Nathan, Marcus Bell, Dana Okafor, Tom Whitfield | At risk | 2026-09-07 | 2027-03-05 | 45% | bar: 2026-09-07 to 2026-11-30
RepApp backend API hardening | Marcus Bell | Marcus Bell, Ravi Menon | On track | 2026-09-07 | 2026-12-04 | 60% | bar: 2026-09-07 to 2026-11-30
Application portfolio dashboard | Dana Okafor | Dana Okafor, Ellen Vargas | On track | 2026-09-21 | 2026-11-20 | 70% | bar: 2026-09-21 to 2026-11-16
Rep chat assistant - discovery | Grace Lin | Grace Lin, Omar Haddad | Not started | 2026-12-14 | 2027-04-09 | 0%
Quality gate remediation | Tom Whitfield | Tom Whitfield, Ravi Menon | On track | 2026-09-07 | 2027-01-29 | 30% | bar: 2026-09-07 to 2026-11-30
Sample row - delete me | Ellen Vargas | Ellen Vargas, Omar Haddad | Complete | 2026-09-07 | 2026-10-23 | 100% | bar: 2026-09-07 to 2026-10-19

## People Load
Who is on what, week by week
Counts concurrent projects per person. Two at once is amber, three or more is red.
 | time axis 2026-09-07 to 2027-08-30
|  |  | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
Person | Role | Projects | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
Priya Nathan | Tech lead | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marcus Bell | Senior engineer | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dana Okafor | Senior engineer | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ravi Menon | Engineer | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ellen Vargas | Engineer | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tom Whitfield | SDET | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grace Lin | UX | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Omar Haddad | Engineer | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names come from the Setup tab. Spelling must match the Team column on Year Plan.

## Milestones
Milestones
Dated commitments behind the bars. Week is calculated from your start date.
Project | Milestone | Owner | Date | Week | Status | Notes
RepApp modernization - remaining 55% | Check contribution front end live in production | Priya Nathan | 2026-09-30 | 4 | Off track | Hard date; other contribution types follow incrementally
RepApp backend API hardening | All supporting APIs delivered and documented | Marcus Bell | 2026-10-17 | 6 | On track
Application portfolio dashboard | Power BI view shared with peer managers | Dana Okafor | 2026-11-06 | 9 | On track